## Sheet1
Start date | Start date | Start date | End date
2018-02-24 | Draw .P. plan | 2 | 2018-02-24
2018-02-25 | Product research | 3 | 2018-02-25
2018-02-26 | Finding images | 3 | 2018-02-26
2018-02-27 | index.html | 3 | 2018-02-27
2018-02-28 | index's css | 3 | 2018-02-28
2018-03-01 | contact MJ | 1 | 2018-03-01
2018-03-02 | review html & css | 4 | 2018-03-02
2018-03-03 | about.html /css | 4 | 2018-03-03
2018-03-04 | How it's made. | 4 | 2018-03-04
2018-03-05 | html / css -how | 4 | 2018-03-05
2018-03-06 | Media queries | 1 | 2018-03-06
2018-03-07 | github | 2 | 2018-03-07
2018-03-08 | invite MJ | 1 | 2018-03-08
2018-03-09 | upload to site | 1 | 2018-03-09
2018-03-10 | write report | 2 | 2018-03-10
38

## Sheet2
Start date | Tasks | Duration / Hour | End date | Overlap by hour | Performer | Meeting
2018-02-24 | Draw .P. plan | 2 | 2018-02-25 |  | Front-end developer
2018-02-25 | Product research | 3 | 2018-02-25 | 1.5 | Front-end developer
2018-02-26 | Finding images | 6 | 2018-03-01 | 3 | Front-end developer
2018-02-27 | index.html | 3 | 2018-02-28 |  | Front-end developer
2018-02-28 | index's css | 3 | 2018-03-01 |  | Front-end developer
2018-03-01 | Review images | 3 | 2018-03-02 |  | Front-end developer | customer-meeting
2018-03-02 | Review html & css | 10 | 2018-03-10 | 10 | Front-end developer
2018-03-03 | About.html /css | 4 | 2018-03-04 |  | Front-end developer
2018-03-04 | Our product.html / css | 4 | 2018-03-05 |  | Front-end developer
2018-03-05 | Contact-Us html / css | 4 | 2018-03-06 |  | Front-end developer
2018-03-06 | Contact MJ | 1 | 2018-03-07 | 0 | Front-end developer
2018-03-06 | Media queries | 1 | 2018-03-07 | 0 | Front-end developer
2018-03-07 | Github | 2 | 2018-03-08 |  | Front-end developer
2018-03-08 | Invite MJ | 1 | 2018-03-09 | 1 | Front-end developer
2018-03-09 | Upload to site | 1 | 2018-03-10 |  | Front-end developer
2018-03-10 | Write report | 3 | 2018-03-10 |  | Front-end developer
51